Incident Information

Incident Action Plan 
Template Example

| Incident Name/ID: | 2025-WATER-001 | Date: | 7/12/2025 |
| --- | --- | --- | --- |
| Incident Type: | Facility Emergency – Water Main Break | Location: | Main Building A, Floor 1 |
| Operational Period: | 7/12/2025 – 7/14/2025 | Prepared by: | Guadalupe Garcia, HR Director |

Objectives:

 Ensure employee safety and prevent entry to water-damaged areas  Maintain business continuity by relocating staff to remote work  Coordinate repair with the city water utility and building management  Resume normal operations within 72 hours

Action Plan:

| Task | Person or Team Responsible | Resources | Timeline/Schedule |
| --- | --- | --- | --- |
| Shut off water to the affected area | Building Maintenance | Access to the utility control room | 7/12/2025 @ 9 AM |
| Notify staff and transition to remote work | HR Department | Company text alert system, Teams, email | 7/12/2025 @ 10 AM |
| Contact city utility and file report | Facility Manager | Local utility contact list, incident log | 7/12/2025 @ 10:30 AM |

Roles and Responsibilities:

| Name & Title | Responsibilities | Phone | Email |
| --- | --- | --- | --- |
| Krista Ahmed, HR Director | Staff communication, safety notifications | 555-123-0000 | kahmed@email.com |
| Romy Bailey, Facility Manager | Coordinate with utilities and vendors | 555-123-1111 | rbailey@email.com |
| Leigh Gibbs, Office Administrator | Data backup integrity, network access | 555-123-1234 | lgibbs@email.com |

Communication Plan:

Internal Employees: Alert via company text system, email, and Teams message from HR by 10:00 AM on July 12 City Utility Department: Facility Manager to call emergency utility line at 512-555-4000 and submit written incident report Building Owner/Management: Written report emailed by 11:00 AM; phone follow-up by 2:00 PM Insurance Provider: Submit incident documentation and initial photos by July 13

Incident Mapping:

- Mark entrances blocked due to flooding. - Mark staging area for cleanup crews near back loading dock.

Incident Action Plan Template

Incident Information

| Incident Name/ID: |  | Date: |  |
| --- | --- | --- | --- |
| Incident Type: |  | Location: |  |
| Operational Period: |  | Prepared by: |  |

Objectives:

Explain the goals that need to be met during and after the incident.

Action Plan:

| Task | Person or Team Responsible | Resources | Timeline/Schedule |
| --- | --- | --- | --- |

Roles and Responsibilities:

| Name & Title | Responsibilities | Phone | Email |
| --- | --- | --- | --- |

Communication Plan:

List who will be informed about the incident and how they will be informed.

Incident Mapping:

Maps, diagrams, visual aids

DISCLAIMER Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.