**[A blue and white sign

AI-generated content may be incorrect.](https://www.smartsheet.com/try-it?trp=12401&utm_source=template-word&utm_medium=content&utm_campaign=SEO)Simple Action Plan Template Example**

|  |  |  |
| --- | --- | --- |
| **Project Name** |  | **Start Date** |
| Spring Donor Engagement Event |  | February 3, 2025 |
|  |  |  |
| **Project Manager** |  | **End Date** |
| Henry McNeal |  | April 5, 2025 |

|  |  |
| --- | --- |
| Goal | Plan a fundraising event for May 10, 2025, to engage key donors for the new wing. |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action Steps | Assigned Person / Team | Priority Level | Status | Resources | Due Date | Notes |
| Confirm event theme and location | Events Team | **High** | Complete | Venue database, event calendar | 10-Feb | Selected rooftop gallery space with panoramic views |
| Develop invitation list | Development Team | **High** | Complete | Donor CRM, board referrals | 14-Feb | Include top 50 major donors and 20 new prospects |
| Design and send invitations | Marketing Team | **Medium** | In Progress | Graphic designer, email software | 28-Feb | Invitations will include link to RSVP + donation options |
| Coordinate catering and entertainment | Events Team | **Medium** | Not Started | Preferred vendors list | 15-Mar | Considering live jazz trio and local catering partner |
| Prepare talking points for staff and board | Development Director | **Medium** | Not Started | Campaign case statement | 25-Mar | Tailor to emphasize impact of new wing |
| Confirm RSVP list and send reminders | Development Assistant | **High** | Not Started | RSVP software | 5-Apr | Use scheduled email and follow-up calls |
|  |  |  |  |  |  |  |

**Simple Action Plan Template**

|  |  |  |
| --- | --- | --- |
| **Project Name** |  | **Start Date** |
|  |  |  |
|  |  |  |
| **Project Manager** |  | **End Date** |
|  |  |  |

|  |  |
| --- | --- |
| Goal |  |

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Action Steps | Assigned Person / Team | Priority Level | Status | Resources | Due Date | Notes |
|  |  | **High** | Complete |  |  |  |
|  |  | **Medium** | Not Started |  |  |  |
|  |  | **Low** | In Progress |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |

**DISCLAIMER**

Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.