## EXAMPLE - Simple Action Plan
Simple Action Plan Template Example
Project Name |  |  | Start Date
Spring Donor Engagement Event |  |  | February 3, 2025
Project Manager |  |  | End Date
Henry McNeal |  |  | 2025-04-05
Goal | Plan a fundraising event for May 10, 2025 to engage key donors for the new wing.
Action Steps | Assigned Person / Team | Priority Level | Status | Resources | Due Date | Notes
Confirm event theme and location | Events Team | High | Complete | Venue database, event calendar | 2025-02-10 | Selected rooftop gallery space with panoramic views
Develop invitation list | Development Team | High | Complete | Donor CRM, board referrals | 2025-02-14 | Include top 50 major donors and 20 new prospects
Design and send invitations | Marketing Team | Medium | In Progress | Graphic designer, email software | 2025-02-28 | Invitations will include link to RSVP + donation options
Coordinate catering and entertainment | Events Team | Medium | Not Started | Preferred vendors list | 2025-03-15 | Considering live jazz trio and local catering partner
Prepare talking points for staff and board | Development Director | Medium | Not Started | Campaign case statement | 2025-03-25 | Tailor to emphasize impact of new wing
Confirm RSVP list and send reminders | Development Assistant | High | Not Started | RSVP software | 2025-04-05 | Use scheduled email and follow-up calls
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Simple Action Plan
Simple Action Plan Template
Project Name |  |  | Start Date
Project Manager |  |  | End Date
Goal
Action Steps | Assigned Person / Team | Priority Level | Status | Resources | Due Date | Notes
|  | High | Complete
|  | Medium | In Progress
|  | Low | Not Started

## Dropdown Key - Do Not Delete
DROPDOWN KEY - DO NOT DELETE
PRIORITY KEY | STATUS KEY
Low | Complete
Medium | Not Started
High | In Progress

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.