## EX - Project Crashing Dash
PROJECT CRASHING DASHBOARD
User to complete the Project Crashing Data Table below. Roadmap and Dashboard Data will populate automatically.
QTR | YEAR |  | AVERAGE TIME TO RESOLUTION in days |  |  |  |  | TARGET TIME TO RESOLUTION
Q4 | 20XX |  | 9.4667 |  |  |  |  | 10
AVERAGE TASK COMPLETION |  |  | STATUS OF PLANNED AUDITS
62%
AUDIT RESULTS
PROJECT CRASHING ROADMAP
PROJECT CRASHING DASHBOARD DATA
ID | DESCRIPTION | % COMPLETE | RESPONSIBLE | START DATE | END DATE | DURATION in days | STATUS | RISK | COMMENTS
1 | Task 1 | 60% | Frank C. | 2028-01-16 | 2028-02-01 | 17 | In Progress | Critical
2 | Task 2 | 30% | Jacob S. | 2028-01-31 | 2028-02-02 | 3 | In Progress | Moderate
3 | Task 3 | 0% | Jacob S. | 2028-02-05 | 2028-02-08 | 4 | Not Started | Critical
4 | Task 4 | 100% | Alex B. | 2028-01-22 | 2028-01-29 | 8 | Complete | Minimal
5 | Task 5 | 80% | Frank C. | 2028-01-28 | 2028-01-31 | 4 | In Progress | Minimal
6 | Task 6 | 0% | Shari W. | 2028-01-29 | 2028-02-25 | 28 | Not Started | Moderate
7 | Task 7 | 100% | Alex B. | 2028-02-28 | 2028-03-01 | 3 | Complete | Moderate
8 | Task 8 | 100% | Kennedy K. | 2028-02-28 | 2028-03-04 | 6 | Complete | Critical
9 | Task 9 | 50% | Jacob S. | 2028-03-01 | 2028-03-16 | 16 | In Progress | Minimal
10 | Task 10 | 100% | Jacob S. | 2028-03-16 | 2028-03-17 | 2 | Complete | Critical
11 | Task 11 | 70% | Jacob S. | 2028-03-18 | 2028-03-20 | 3 | In Progress | Minimal
12 | Task 12 | 25% | Alex B. | 2028-03-24 | 2028-04-10 | 18 | in Progress | Critical
13 | Task 13 | 100% | Shari W. | 2028-03-24 | 2028-03-26 | 3 | Complete | Minimal
14 | Task 14 | 30% | Shari W. | 2028-03-26 | 2028-04-05 | 11 | In Progress | Critical
15 | Task 15 | 85% | Kennedy K. | 2028-04-06 | 2028-04-21 | 16 | In Progress | Critical
DATA TALLIES
Data Tallies will calculate automatically. Do not alter.
| STATUS | TOTAL |  |  |  |  | RISK | TOTAL
| Not Started | 2 |  |  |  |  | Minimal | 5
| In Progress | 8 |  |  |  |  | Moderate | 3
| Complete | 5 |  |  |  |  | Critical | 7
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Project Crashing Dash
PROJECT CRASHING DASHBOARD
User to complete the Project Crashing Data Table below. Roadmap and Dashboard Data will populate automatically.
QTR | YEAR |  | AVERAGE TIME TO RESOLUTION in days |  |  |  |  | TARGET TIME TO RESOLUTION
Q4 | 20XX |  | – |  |  |  |  | 0
AVERAGE TASK COMPLETION |  |  | STATUS OF PLANNED AUDITS
–
AUDIT RESULTS
PROJECT CRASHING ROADMAP
PROJECT CRASHING DASHBOARD DATA
ID | DESCRIPTION | % COMPLETE | RESPONSIBLE | START DATE | END DATE | DURATION in days | STATUS | RISK | COMMENTS
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
DATA TALLIES
Data Tallies will calculate automatically. Do not alter.
| STATUS | TOTAL |  |  |  |  | RISK | TOTAL
| Not Started | 0 |  |  |  |  | Minimal | 0
| In Progress | 0 |  |  |  |  | Moderate | 0
| Complete | 0 |  |  |  |  | Critical | 0
Right-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | RISK | STATUS
Yes | Minimal | Not Started
No | Moderate | In Progress
| Critical | Complete

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.