## EXAMPLE - Event Timeline
Event Timeline Template Example
Event Name |  | Event Type | [7 empty] | Date
Location |  | Description
Key Contacts
Name: |  | Role: | Phone: | [6 empty] | Email:
Name: |  | Role: | Phone: | [6 empty] | Email:
Name: |  | Role: | Phone: | [6 empty] | Email:
|  |  | Phase One |  |  | PHASE TWO |  |  | PHASE TWO | Phase Two |  |  | Phase Three |  |  | Phase Four |  |  | Phase Five |  |  | Phase Six
Task | Additional Info | Assigned To | Wk1 1 | Wk1 2 | Wk 3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18
Phase 1: Initial Planning
Define event goals
Set preliminary budget
Identify stakeholders
Research venues and vendors
Draft preliminary schedule
Phase 2: Detailed Planning
Finalize venue
Confirm event date
Assign team roles
Create detailed budget
Submit permits or insurance (if needed)
Phase 3: Booking & Logistics
Book vendors (catering, AV, rentals, etc.)
Finalize agenda or run-of-show
Coordinate transportation and accommodations
Order materials (badges, signage, décor, etc.)
Conduct risk assessment
Phase 4: Promotion & Prep
Launch invitations or registration
Promote via social media, email, etc.
Finalize guest list
Print materials
Walk-through or dry run
Phase 5: Event Execution
Setup venue
Confirm vendor arrivals
Run check-in or registration
Monitor event flow
Handle issues as needed
Phase 6: Post-Event
Break down and clean up
Send thank-you notes
Conduct internal debrief
Review budget vs actuals
Send post-event survey
Notes
General Notes
Outstanding Notes
Lessons Learned
CLICK HERE TO CREATE IN SMARTSHEET | bar: Wk 3 to Phase Five Wk 15
Event Date
Define event goals
Set preliminary budget
Identify stakeholders
Finalize venue and confirm event date
Assign team roles
Create detailed budget
Book vendors (catering, AV, rentals, etc.)
Finalize agenda or run-of-show
Coordinate transportation and accommodations
Launch invitations or registration
Promote via social media, email, etc. and finalize guest list
Print Materials
Walk-through or dry run
Setup Venue
Confirm vendor arrivals and run check-in or registration
Monitor event flow
Break down and clean up and send thank-you notes
Conduct internal debrief and Review budget vs actuals
Send post-event survey
Handle issues needed
Resarch venues and vendors
Draft preliminary schedule
Submit permits or insurance (if needed)
Order materials (badges, signage, décor, etc.)
Conduct risk assessment

## BLANK - Event Timeline
Event Timeline Template
Event Name |  | Event Type | [7 empty] | Date
Location |  | Description
Key Contacts
Name: |  | Role: | Phone: | [6 empty] | Email:
Name: |  | Role: | Phone: | [6 empty] | Email:
Name: |  | Role: | Phone: | [6 empty] | Email:
|  |  | Phase One |  |  | PHASE TWO |  |  | PHASE TWO | Phase Two |  |  | Phase Three |  |  | Phase Four |  |  | Phase Five |  |  | Phase Six
Task | Additional Info | Assigned To | Wk1 1 | Wk1 2 | Wk 3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16 | Wk 17 | Wk 18
Phase 1: Initial Planning
Phase 2: Detailed Planning
Phase 3: Booking & Logistics
Phase 4: Promotion & Prep
Phase 5: Event Execution
Phase 6: Post-Event
Notes
General Notes
Outstanding Notes
Lessons Learned
Event Date
Send post-event survey

## - Disclaimer -
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.