## Event Marketing Timeline
EVENT MARKETING TIMELINE
|  | PHASE ONE |  |  | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR
CAMPAIGN TYPE | ADDITIONAL INFO | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12
National Marketing
Banner Ads | bar: PHASE ONE WEEK 1; PHASE ONE WEEK 3; PHASE TWO WEEK 5; PHASE THREE WEEK 7; PHASE THREE WEEK 9; PHASE FOUR WEEK 11
Local Marketing
Web Ads | bar: PHASE ONE WEEK 1 to PHASE TWO WEEK 5; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
Public Relations
Press Releases | bar: PHASE ONE WEEK 3; PHASE THREE WEEK 7; PHASE FOUR WEEK 12
Webinars | bar: PHASE ONE WEEK 1; PHASE TWO WEEK 5; PHASE FOUR WEEK 10
Content Marketing
Sponsored Content | bar: PHASE ONE WEEK 3; PHASE THREE WEEK 7; PHASE FOUR WEEK 11
Landing Page | bar: PHASE ONE WEEK 2; PHASE TWO WEEK 4; PHASE TWO WEEK 6; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
White Papers / ebooks | bar: PHASE ONE WEEK 1; PHASE TWO WEEK 5; PHASE THREE WEEK 9
Social Media
Twitter
Facebook
Pinterest | bar: PHASE ONE WEEK 2; PHASE TWO WEEK 4; PHASE TWO WEEK 6; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
Instagram
Google+ | bar: PHASE ONE WEEK 2; PHASE TWO WEEK 4; PHASE TWO WEEK 6; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
LinkedIn | bar: PHASE ONE WEEK 2; PHASE TWO WEEK 4; PHASE TWO WEEK 6; PHASE THREE WEEK 8; PHASE FOUR WEEK 10; PHASE FOUR WEEK 12
Snapchat | bar: PHASE ONE WEEK 1; PHASE ONE WEEK 3; PHASE TWO WEEK 5; PHASE THREE WEEK 7; PHASE THREE WEEK 9; PHASE FOUR WEEK 11
Online
Blog
Website | bar: PHASE ONE WEEK 1; PHASE ONE WEEK 3; PHASE TWO WEEK 5; PHASE THREE WEEK 7; PHASE THREE WEEK 9; PHASE FOUR WEEK 11
Mobile App | bar: PHASE ONE WEEK 2; PHASE TWO WEEK 4; PHASE THREE WEEK 7; PHASE FOUR WEEK 10
Mobile Alerts | bar: PHASE ONE WEEK 3; PHASE TWO WEEK 6; PHASE THREE WEEK 9; PHASE FOUR WEEK 12
Email Newsletter
Web
Development | bar: PHASE ONE WEEK 1 to PHASE ONE WEEK 3
Pay-Per-Click Marketing | bar: PHASE TWO WEEK 5 to PHASE FOUR WEEK 10
SEO | bar: PHASE ONE WEEK 2 to PHASE TWO WEEK 5
Market Research
Surveys | bar: PHASE ONE WEEK 3; PHASE THREE WEEK 7; PHASE FOUR WEEK 10
Impact Studies | bar: PHASE TWO WEEK 6 to PHASE THREE WEEK 9
Sales Campaigns
Campaign A | bar: PHASE ONE WEEK 1 to PHASE ONE WEEK 3
Campaign B | bar: PHASE TWO WEEK 4 to PHASE TWO WEEK 6
Campaign C | bar: PHASE TWO WEEK 6 to PHASE THREE WEEK 8
Campaign D | bar: PHASE THREE WEEK 8 to PHASE FOUR WEEK 10
Campaign E | bar: PHASE FOUR WEEK 11 to PHASE FOUR WEEK 12
Other
Corporate Branding | bar: PHASE ONE WEEK 2 to PHASE TWO WEEK 4
CLICK HERE TO CREATE IN SMARTSHEET

## BLANK - Event Marketing Tmln
EVENT MARKETING TIMELINE
|  | PHASE ONE |  |  | PHASE TWO |  |  | PHASE THREE |  |  | PHASE FOUR
CAMPAIGN TYPE | ADDITIONAL INFO | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10 | WEEK 11 | WEEK 12
National Marketing
Banner Ads | bar: PHASE ONE WEEK 1
Local Marketing
Web Ads | bar: PHASE ONE WEEK 1
Public Relations
Press Releases | bar: PHASE ONE WEEK 1
Webinars
Content Marketing
Sponsored Content | bar: PHASE ONE WEEK 1
Landing Page
White Papers / ebooks
Social Media
Twitter | bar: PHASE ONE WEEK 1
Facebook
Pinterest
Instagram
Google+
LinkedIn
Snapchat
Online
Blog | bar: PHASE ONE WEEK 1
Website
Mobile App
Mobile Alerts
Email Newsletter
Web
Development | bar: PHASE ONE WEEK 1
Pay-Per-Click Marketing
SEO
Market Research
Surveys | bar: PHASE ONE WEEK 1
Impact Studies
Sales Campaigns
Campaign A | bar: PHASE ONE WEEK 1
Campaign B
Campaign C
Campaign D
Campaign E
Other
Corporate Branding | bar: PHASE ONE WEEK 1

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.